## Slide 1
Salesteq x MYNM
Project Kickoff / March 2026
MYNM AI Platform Kickoff
Software Development Agreement, effective 1 March 2026. Contract value: $372,842 USD.
3.1 INBOUND AI AGENT
Multi-brand AI chat across 13 websites + WhatsApp + Telegram
BMW, MINI, Rolls-Royce, Genesis, Jaguar, Land Rover, Infiniti, Lincoln, Hyundai, Ford, MG
Voice Input: MSA, Najdi, Janoubia dialects, English
Keyloop DMS + inventory feed integration
OTP customer ID, complaints, bookings, VIN queries
Timeline: MVP Month 1, Full Month 3
3.2 OUTBOUND AI SALES
Proactive follow-ups and campaigns
Lead matching: inventory + CRM + Keyloop data
Customer behavior and sentiment-driven triggers
Outbound via WhatsApp or email
Timeline: Month 5
3.3 SALES ENABLEMENT
Internal AI assistant for sales reps and call center
Callback request handling
Trade-in management
Customer sentiment insights
Searchable internal knowledge base
Timeline: Month 6
3.4-3.6 ANALYTICS & DASHBOARDS
Call transcription (EN + MSA), tone analysis, sentiment
Genesys + Webex Contact Center integration
AI analytics: interactions, topics, resolution rates, channels
Live dashboards by brand and division with export
Compliance alerts (Ministry of Commerce)
Timeline: Month 4-5
Confidential
Slide 1 of 2

## Slide 2
Salesteq x MYNM
Project Kickoff / March 2026
Delivery Plan, Payments & Dependencies
Fixed-price milestones. Infrastructure at $3,000/month pass-through. Support at SAR 12,000/month.
MILESTONE
DELIVERABLE
TIMELINE
3.1 Inbound Agent
Multi-brand chat, OTP, Keyloop, voice (AR/EN)
MVP M1 / Full M3
3.2 Outbound Sales
Proactive campaigns, lead matching, WA/email
Month 5
3.3 Sales Enablement
Internal agent, callbacks, trade-in, KB
Month 6
3.4 Call Analytics
Transcription, sentiment, Genesys/Webex
Month 4
3.5 AI Analytics
Engagement, topics, resolution rates
Month 5
3.6 Dashboards
Live reports by brand/division, export
Month 5
PAYMENT SCHEDULE
Upon Contract Signing
$74,568.40
R1: Advanced Sales Chat & Search
$149,136.80
R2: Sales AI
$74,568.40
Call Analytics & Dashboard Delivery
$74,568.40
Total Contract
$372,842.00
INFRASTRUCTURE (PASS-THROUGH)
3x A100 80GB SXM4 GPU instances
$3,000/month at actual consumption, no markup
ASR + TTS + LLM inference (Qwen3, FastConformer, FastPitch)
30,000 users/month, 20 simultaneous requests
SUPPORT (EXHIBIT B)
SAR 12,000/month (20 engineer hrs, Mon-Fri 09-19)
P1 Critical: response 20 min, fix 6 hrs
P2 High: response 45 min, fix 14 hrs
15 months warranty (extended from 12)
20 days extra engineering in first month
NEEDED FROM MYNM
Keyloop API access, credentials, and documentation
Inventory feed access for all brands
Genesys / Webex Contact Center access
WhatsApp Business API (Hootsuite) access
Car metadata: specs, options, media per brand
OTP phone verification setup
Brand guidelines (CSS, fonts, colors) per brand
Confidential
Slide 2 of 2